## Title Page
FY 2019 Call for Projects
Regional Traffic Signal Synchronization Program
Project P
<SAMPLE> Supplemental Application
El Toro Road
2018-10-18
| Applicant Agency: | City of | Lake Forest
| Contact Name: | John Doe
| Contact Number: | 949-567-1234
| Contact Email: | John.Doe@city.gov
Note on A13: Input Name of Corridor
Note on F36: Input Name of Applicant Agency
Note on E38: Input Applicant Agency Contact Person
Note on E40: Input Applicant Agency Contact Phone Number
Note on E42: Input Applicant Agency Contact Email

## Checklist
Project P Regional Traffic Signal Synchronization Program Application Checklist
Project P Application Checklist | Page
RTSSP Online Application – submitted through OCFundTracker | Online
1. Vehicle Miles Traveled
2. Benefic Cost Ratio
3. Project Characteristics
4. Transportation Significance
5. Maintenance of Effort
6. Project Scale
7. Number of Jurisdictions
8. Current Project Readiness
9. Funding Over-Match
10. Cabinet photos, equipment specifications, as-built drawings, cabinet drawings, etc. (if OCTA-Led) | Flashdrive
Section 1: Key Technical Information
a. Project Corridor Limits | 1
b. Designation of the corridor to synchronize: Signal Synchronization Network corridor or Master Plan of Arterial Highways corridor | 1
c. Project start date and end date, including any commitment to operate signal synchronization beyond the three year grant period | 1
d. Signalized intersections that are part of the project | 1
e. Traffic Forum members | 1
Section 2: Lead agency | 2
Section 3: Resolutions of support from the project’s Traffic Forum members | 3
Section 4: Preliminary plans for the proposed project by task (detail below)
The plans shall include details about both phases of the project: Primary Implementation (PI) and the Ongoing Maintenance and Operations (O & M). The plan should be organized using the following setup.
Primary Implementation shall include details about the following:
Task 1: Project Administration (required) | Pg. 4-5
Task 2: Data Collection (required)
Task 3: Field Review and Plans Specifications and Estimates (required)
Task 4: Corridor "Before" Study (required)
Task 5: Signal Timing Optimization and Implementation (required)
Task 6: Corridor "After" Study (required)
Task 7: Sychronization System Construction (required)
Task 8: Project Report (required)
Task 9: On-going Operations and Maintenance (required)
Ongoing Maintenance and Operations (O&M) shall begin after the Primary Implementation of the project is completed. It shall include details about the following: | Pg. 6
a. Monitoring and improving optimized signal timing (required)
b. Communications and detection support (optional)
c. O&M Final Memorandum (required)
Section 5: Funding Needs/Costs for Proposed Project by Task | Pg. 6
a. Table I: Summary of Improvements | Pg. 7
b. Table II: Detailed Improvement Breakdown | Pg. 8
Section 6: Project schedule for the 3 year grant period by task | Pg. 9
Section 7: Matching funds | Pg. 10
Section 8: Environmental clearances and other permits | Pg. 11
Section 9: Calculations used to develop selection criteria inputs | Pg. 11-12
Section 10: Any additional information deemed relevant by the applicant | Pg. 13
Appendices | Pg. 14

## Section 1
SECTION 1: KEY TECHNICAL INFORMATION
a. | The proposed project will synchronize El Toro Road from Bridger Road to Valley Vista Way. The project includes twenty (20) signals over seven (7) miles. Figure 1 shows a map of the project area.
Figure 1: Signalized intersection and proposed project limits.
b. | Designation of the corridor to synchronize:
c. | Project Start Date: |  | Project End Date:
All agencies commit to operate signal sychronization BEYOND the three year grant period for:
d. | Signalized intersections that are part of the project:
City of Lake Forest
| 1. El Toro Road @ Bridger |  |  | 12. El Toro Road @ Normandale Drive
| 2. El Toro Road @ Rockfield Boulevard |  |  | 13. El Toro Road @ Portola Parkway
| 3. El Toro Road @ Arbor Way |  |  | 14. El Toro Road @ Pheasant Run
| 4. El Toro Road @ Raymond Way |  |  | 15. El Toro Road @ Ridgeline Drive
| 5. El Toro Road @ Muirlands Boulevard |  |  | City of Mission Viejo
| 6. El Toro Road @ Jeronimo Road |  |  | 16. El Toro Road @ Marguerite Parkway
| 7. El Toro Road @ Toledo Way |  |  | 17. El Toro Road @ Painted Trails
| 8. El Toro Road @ Serrano Road |  |  | 18. El Toro Road @ Wandering Trails
| 9. El Toro Road @ Trabuco Road |  |  | 19. El Toro Road @ Glenn Ranch Road
| 10. El Toro Road @ Aliso Park Drive |  |  | County of Orange
| 11. El Toro Road @ Northcrest Drive |  |  | 20. El Toro Road @ Valley Vista Way
e. | Traffic Forum members: | Lake Forest
Mission Viejo
County of Orange
City of Laguna Hills
Zero Years
One Year
Two Years
Three Years
Other
Master Plan of Arterial Highways Corridor
Signal Synchronization Network Corridor

## Section 2
SECTION 2: LEAD AGENCY
| City of |  | will be the lead agency
County of Orange will be the lead agency
X | OCTA is requested to be the lead agency and the following items SHALL be included as part of this application either by CD/DVD/flash drive or uploaded to OCFundtracker:
1. Available as-built for entire project corridor
2. Cabinet photos
3. Cabinet drawings
4. Current City Specifications, including, but not limited to:
| a. | Cabinet specifications (Specify type and # of detector racks and other specific requirements desired)
| b. | Controller preferences (e.g. Cobalt w/o touch screen running ASC/3 firmware)
| c. | Ethernet switch preferences (Specify # of ports needed)
| d. | CCTV preferences
| e. | Video detection preferences
| f. | Fiber strand count (regular or armored), length of drop cable
| g. | Pullbox preferences (e.g. #6 or 6E; concrete or Fiberlyte; etc.)
| h. | Other specific requirements by the Agencies, such as Video inspection, etc.

## Section 3
SECTION 3: RESOLUTIONS OF SUPPORT
Resolutions of support from Traffic Forum members are provided on the following pages.
Orange County Regional Traffic Signal Synchronization Program Projects
A resolution of the _______________ City Council approving the submittal of ________________ improvement project(s) to the Orange County Transportation Authority for funding under the competitive Measure M2 Regional Traffic Signal Synchronization Program.
THE CITY COUNCIL OF THE CITY OF _________ HEREBY RESOLVES, DETERMINES, AND ORDERS AS FOLLOWS THAT:
(a) WHEREAS, the Measure M2 Regional Traffic Signal Synchronization Program targets over 2000 signalized intersections across Orange County to maintain traffic signal synchronization, improve traffic flow, and reduce congestion across jurisdictions; and
(b) WHEREAS, the City of __________ has been declared by the Orange County Transportation Authority to meet the eligibility requirements to receive revenues as part of Measure M2; and
(c) WHEREAS, the City must include all projects funded by Net Revenues in the seven-year Capital Improvements Program as part of the Renewed Measure M Ordinance eligibility requirement.
(d) WHEREAS, the City authorizes a formal amendment to the seven-year Capital Improvement program to add projects approved for funding upon approval from the Orange County Transportation Authority Board of Directors, if necessary.
(e) WHEREAS, the City of __________ has a currently adopted a Local Signal Synchronization Plan consistent with the Regional Traffic Signal Synchronization Master Plan as a key component of local agencies’ efforts to synchronizing traffic signals across local agencies’ boundaries; and
(f) WHEREAS, the City of __________ will provide matching funds for each project as required by the Orange County Comprehensive Transportation Funding Programs Procedures Manual; and
(g) WHEREAS, the City of __________ will not use Measure M funds to supplant Developer Fees or other commitments; and
(h) WHEREAS, the City of __________ desires to implement multi-jurisdictional signal synchronization listed below; and
NOW, THEREFORE, BE IT RESOLVED THAT:
The City Council of the City of __________ hereby requests the Orange County Transportation Authority allocate funds in the amounts specified in the City's application to said City from the Regional Traffic Signal Synchronization Program. Said funds, if approved, shall be matched by funds from said City as required and shall be used as supplemental funding to aid the City if signal synchronization along the following street(s):
ADOPTED BY THE CITY COUNCIL on ____________________, 20____.
SIGNED AND APPROVED on ____________________, 20____.
_________________
City Clerk
_________________
Mayor
"Sample
Resolution"
Exhibit 8-2
Form

## Section 4
SECTION 4: PRELIMINARY PLANS FOR THE PROJECT
Primary Implementation (PI)
The Primary Implementation phase will last approximately one year and include the following elements:
Task 1: | Project Administration
<SAMPLE TEXT> OCTA will lead the project using contracted consultant staff to optimize signal synchronization timing along the El Toro Road corridor. OCTA shall perform normal day to day project administration duties. Local agency staff will perform local project administration duties. Project budget shall include time and funding for agency outreach and coordination.
Task 2: | Data Collection
<SAMPLE TEXT> The OCTA Consultant will collect data necessary to thoroughly understand existing traffic conditions in the study area and be able to develop optimal time-of-day traffic signal coordination plans, if applicable.
Task 3: | Field Review and Plans Specifications, and Estimates
<SAMPLE TEXT> OCTA will use qualified traffic engineering consultants to complete the engineering design of the fiber upgrade and communications for the project. The Consultant will review the geometric layout, existing traffic signal equipment, and signal synchronization related infrastructure to identify any deficiencies for each intersection and along the whole corridor/route. The review shall include an assessment of the existing intersection geometry, traffic conditions, traffic signal control equipment, and telemetry/interconnect facilities along the corridor and of each intersection using observation, available as-built plans, consultation with the local AGENCIES, and Party supplied aerial photos. With permission of the local AGENCIES, CONSULTANT shall inspect the interior of each traffic control cabinet, inspect the telemetry systems and determine their respective condition and make recommendations for equipment upgrades.
Task 4: | Corridor "Before" Study
<SAMPLE TEXT> OCTA will use qualified traffic engineering consultants to conduct "before" floating car travel runs prior to timing implementation. The Consultant will conduct a ‘Before’ field study report representative of the times and days for which synchronization plans will be developed. The report shall identify Measures of Effectiveness (MOE) to evaluate the effects of the synchronization plans. MOE’s will likely include traffic flow, travel time, average speed, number of stops per mile, number of intersections traversed on green vs. stopped by red (Greens per Red) (note: Average Speed, Stops per Mile, and Greens per Red are the new OCTA MOE, Corridor Synchronization Performance Index (CSPI)), fuel consumption reduction, pollution reduction, and other pertinent items.
Task 5: | Signal Timing Optimization and Implementation
<SAMPLE TEXT> Synchronization will be inter-jurisdictional in nature. All existing traffic patterns, flows, and conditions will be taken into account. Synchronized timing will be developed for the AM Peak, PM Peak, Mid-day Peak and Weekend Peak. Special generators such as schools and businesses along with cross street traffic will be considered as part of the project. Timing plans will be developed that assist traffic in getting to its destination without regard to physical or political boundaries.
Task 6: | Corridor "After" Study
<SAMPLE TEXT> OCTA will use qualified traffic engineering consultants to conduct "after" floating car travel runs after timing implementation. The Consultant will conduct an ‘After’ field study representative of the times and days for which synchronization plans will be developed. The ‘After’ study must be conducted in the same manner and contain the same MOE’s as the ‘Before’ study in order to evaluate the improvements of the synchronization plans. MOE’s should be compiled for the optimized corridor using the floating car method.
Task 7: | Synchronization System Construction
<SAMPLE TEXT> OCTA will use qualified traffic engineering consultants and contractors to design, procure, and install equipment upgrades based on Section 5. All installations and upgrades will be per the owning agencies' standards. Details of equipment upgrades are tabulated in Tables I and II. Since the agencies have requested OCTA to be the lead on this project, the required documents are included on the accompanied flash drive.
Task 8: | Project Report
<SAMPLE TEXT> The contracted consultant will develop a before and after study for the project. This report will be completed after the Primary Implementation is completed and will include the following: • Introduction/project description: a summary of the project including the purpose, background, and objectives of the project. • Data collection: a summary of the data collected as part of the effort including the traffic counts, phasing, lane configurations, etc. • Traffic signal systems improvements: a summary of the implemented traffic signal systems improvements by city. • Signal timing optimization: a summary of the development and implementation of updated signal timing including the models, selected cycle lengths, intersection groupings, etc. • Results: the study will contain directional morning, mid-day, evening, and weekend peak periods using travel times, average speeds, green lights to red lights, stops per mile, and the derived corridor synchronization performance index (CSPI) metric. This information shall be collected both before and after any signal timing changes have been made. Additional details based on the Final Report Template will also be included. • Benefits to cost analysis: project benefits resulting from signal synchronization will be evaluated based on the before and after study results. Savings will be calculated for travel time, fuel consumptions, vehicle maintenance, Greenhouse Gas (GHG) reduction, and a final benefit cost ratio. • Future signal corridor improvements: recommendations for system and equipment enhancements to improve traffic flow and signal synchronization will be provided. • Conclusion: a summary of the before and after study and its findings.
Task 9: | On-going Maintenance & Operations
<SAMPLE TEXT> The Consultant shall provide “on-call” signal timing support services for a period of two years or 24 months following the implementation and fine – tuning of the final signal timing plans, Task 5, to address any future adjustments that may be needed during this period. Depending on the nature of the adjustment, the Consultant may accomplish the fine-tuning adjustments remotely from the office through the traffic management systems. During this 24-month period the Consultant will be prepared to review any project intersection requested within (24) hours of written notice, including observing and fine-tuning the signal timing. The Consultant will also assist with resovling detection issues along the corridor. The Consultant will drive the length of the project arterial during all designated corridor synchronization timing plan hours of operation on a monthly basis in order to verify that the synchronization timing is working as designed, and complete any necessary adjustments. Monthly driving times will consist of a full 12-hour weekday and a 4-hour Saturday. All drives shall be documented. A copy, limited to political boundaries, shall also be sent to each agency. At the end of the 2-year O&M phase, the Consultant shall prepare a memoradum to summarize the O&M phase. It should, at the minimum, include when travel runs were conducted, issues and solutions throughout the phase, and recommendations for future improvements.

## Section 5
SECTION 5: FUNDING NEEDS/COSTS FOR PROPOSED PROJECT BY TASK
Primary Implementation
The Primary Implementation will last one year and include the following elements (See Table I and Table II). INSTRUCTIONS: Be sure to carefully review improvements that may need engineering design or develoment of specifications prior to construction. For example, the interconnect conduit installation, new service locations, or cabinet foundations. Include this cost in your estimate. Costs associated with Caltrans fees, SCE fees, and/or special inspection requirements should also be included.
Project Tasks |  |  | Total Cost | Match
|  |  |  | Cash | In-Kind
Task 1: Project Administration |  |  | 20000 | 2302 | 1698
Task 2: Data Collection |  |  | 9000 | 1800 | 0
Task 3: Field Review and Plans Specifications, and Estimates |  |  | 10509 | 20177.8 | 324
Task 4: Corridor "Before" Study |  |  | 5000 | 1000 | 0
Task 5: Signal Timing Optimization and Implementation |  |  | 80000 | 14694 | 1306
Task 6: Corridor "After" Study |  |  | 5000 | 1000 | 0
Task 7: Synchronization System Construction (See Table II) |  |  | 1111050 | 197210 | 25000
Task 8: Project Report |  |  | 10000 | 2000 | 0
Task 9: Ongoing Operations & Maintenance (See Task 9 Details) |  |  | 48000 | 9600 | 0
Total Project Cost: |  |  | 1298559 | 249783.8 | 28328
Ongoing Operations & Maintenance
Ongoing Operations and Maintenance will last two years and include the following elements. (See Task 9 Details below)
Task 9 Details:
Task | Description of Work |  | Unit Price / Intersection | # of signals | Cost
Monitoring and improving optimized signal timing | Drive monthly and improve timing parameters along 20 signals for 24 months after signal timing and implemented along El Toro Road from Bridger Rd to Ridgeline Rd (@$70/signal/month) |  | 1680 | 20 | 33600
Communications and detection support | Monitor, maintain, and repair communication and detection along for 20 signals for 24 months after signal timing is implemented along El Toro Road from Bridger Rd to Ridgeline Rd. (@ $30/signal/month) |  | 720 | 20 | 14400
Proposed Onging Operations & Maintenance: |  |  |  |  | 48000
Total Project Cost (Including PI and O&M for a total of 3 years):
Total
|  | Total M2 Request: |  | 1038847.2
|  | Total Agency Match: |  | 278111.8
|  | Total Project Cost: |  | 1298559

## Table GUIDELINES
PART I: GUIDELINES ON HOW TO FILL OUT THE "TABLE I-SUMMARY OF IMPROVEMENTS" TAB
1. ADD THE STREET NAME AT THE TOP OF THE WORK PLAN SHEET
2. ADD THE STREET NAME, AGENCY, AND PROJECT INTERSECTION
3. ADD AN "X" IF EQUIPMENT IS TO BE INSTALLED AT THAT LOCATION
PART 2: GUIDELINES ON HOW TO FILL OUT THE "TABLE II-IMPROVEMENTS BREAKDOWN" TAB
1. ADD ITEM NUMBERS AND STREET NAME WHERE EQUIPMENT IS TO BE INSTALLED. DO NOT LUMP IMPROVEMENTS.
2. ADD THE ITEM DESCRIPTION AND INCLUDE ALL COMPONENTS TO BE INSTALLED.
3. EACH ITEM MUST HAVE A UNIT, QUANTITY, ESTIMATED COST OF LABOR AND EQUIPMENT, AND MATCH AMOUNT.
4. ADD THE OWNING AGENCY.
5. ADD CONTINGENCY AND CONSTRUCTION MANAGEMENT (OPTIONAL).
6. SUM UP ALL TOTALS IN THE LAST ROW.
7. MAKE ALL FORMULAS AND MATCH AMOUNT ARE CORRECT.
PART 3: GUIDELINES ON HOW TO FILL OUT THE "MATCH" TAB
1. ADD THE AMOUNT AGENCY WILL CONTRIBUTE IN CASH TO BOTH PI AND OMM PHASES IN SECTION 1
2. ADD THE FUNDING SOURCE AND TOTAL CASH CONTRIBUTED PER AGENCY IN SECTION 2A
3. ADD ANY SPECIFIC IMPROVEMENTS AGENCY WILL CONTRIBUTE AS IN-KIND TO SECTION 2B(i)
4. ADD DETAILS, HOURS, AND RATE OF STAFFING COMMITMENT AS IN-KIND SERVICES TO SECTION 2B(ii)
FOR QUESTIONS, CONTACT AMY TRAN (ATRAN@OCTA.NET) OR ANTONIO MAGANA (AMAGANA@OCTA.NET)

## Table I-SUM of IMPROVE
TABLE II: SUMMARY OF IMPROVEMENTS
Location | Agency | Project Intersections at: | Description of Work
|  |  | INTERSECTION | [5 empty] | CONTROLLERS |  | CONTROLLER CABINET |  |  |  |  | COMMUNICATION UPGRADE | [7 empty] | ADVANCED TRAFFIC MANAGEMENT SYSTEM (ATMS)
|  |  | EVP (all directions) | Video Detection System | UPS | GPS | ADA Pushbutton Assembly | Pedestrian Countdown Heads | New Controller | SDLC Cable | New Cabinet with New Foundation | New Cabinet (Reuse existing foundation) | System Detector (DLC) | Advance Detection Loop with New Conduit | Bluetooth Travel Time Unit | CCTV Camera | 6E Pullbox and Splice Enclosure | Fiber In New Conduit | Fiber in Existing Conduit | Fiber Distribution Unit (FDU) | Fiber Switch/Ethernet Switch | Patch Panel and Fiber Splicling | Cell Modem | CENTRACS Integration + System Graphics | CENTRACS System License | TMC Workstation
El Toro Road at:
Column1 | Column3 | Column4 | Column5 | Column6 | Column62 | Column622 | Column623 | Column63 | Column64 | Column642 | Column10 | Column13 | Column14 | Column15 | Column16 | Column19 | Column20 | Column21 | Column22 | Column23 | Column232 | Column233 | Column234 | Column24 | Column25 | Column26
1 | Lake Forest | Bridger Road | [5 empty] | x | x | [11 empty] | x
2 | Lake Forest | Rockfield Boulevard | [5 empty] | x | x | [11 empty] | x
3 | Lake Forest | Arbor Way | [5 empty] | x | x | [11 empty] | x
4 | Lake Forest | Raymond Way | [5 empty] | x | x | [11 empty] | x
5 | Lake Forest | Muirlands Boulevard | [5 empty] | x | x | [11 empty] | x
6 | Lake Forest | Jeronimo Road | [5 empty] | x | x | [11 empty] | x
7 | Lake Forest | Toledo Way | [5 empty] | x | x | [11 empty] | x
8 | Lake Forest | Serrano Road | [5 empty] | x | x | [11 empty] | x | bar: Column13
9 | Lake Forest | From Serrano Road to Trabuco Road | bar: Column20; Column22
10 | Lake Forest | Trabuco Road | [5 empty] | x | x | [11 empty] | x
11 | Lake Forest | Aliso Park Drive | [5 empty] | x | x | [11 empty] | x | bar: Column13
12 | Lake Forest | Northcrest Drive | [5 empty] | x | x | [11 empty] | x | bar: Column13
13 | Lake Forest | Normandale Drive | [5 empty] | x | x | [11 empty] | x
14 | Lake Forest | Portola Parkway | [5 empty] | x | x | [11 empty] | x | bar: Column13
15 | Lake Forest | Pheasant Run | [5 empty] | x | x | [11 empty] | x |  | x
16 | Lake Forest | From Trabuco Road to Portola Parkway | bar: Column20 to Column21
17 | Lake Forest | Lake Forest TMC | [22 empty] | x
18 | Mission Viejo | Marguerite Parkway |  |  |  |  | x
19 | Mission Viejo | Painted Trails |  |  |  |  | x
20 | Mission Viejo | Wandering Trails |  |  |  |  | x
21 | Mission Viejo | Glenn Ranch Road |  |  | x |  | x
22 | Mission Viejo | From Marguerite Parkway and Glenn Ranch Road | bar: Column20; Column22
23 | County of Orange | Valley Vista Way |  |  | x |  |  |  | x | [11 empty] | x |  | x | x | bar: Column13
24 | Laguna Hills | Avenida De La Carlotta / El Toro | [6 empty] | x
25 | Laguna Hills | Avenida De La Carlotta / SB Ramps | [6 empty] | x
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67

## Table II-IMPROVE BRKDWN
TABLE II: DETAILED IMPROVEMENTS BREAKDOWN
Item No. | El Toro Road @ | Item Description | Unit | Qty | Labor to Install | Equipment Cost | Labor Rate | Material | Tax | Other Direct Cost | Total | Cash Match | In-Kind Match | Agency | Vendor | Vendor
1 | Bridger Road | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3500 |  |  |  |  | 4050 | 310 | 0 | Lake Forest | Total | Total
2 |  | Furnish & install Actelis ML684DF Ethernet Switch | EA | 1 | 400 | 1100 |  |  |  |  | 1500 | 300 | 0 | Lake Forest | Total | Total
3 |  | Furnish & install Countdown Ped Head System | EA | 6 | 135 | 145 |  |  |  |  | 1680 | 336 | 0 | Lake Forest | Total | Total
4 | Rockfield Boulevard | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3500 |  |  |  |  | 4050 | 310 | 0 | Lake Forest | 0 | 0
5 |  | Furnish & install Actelis ML684DF Ethernet Switch | EA | 1 | 400 | 1100 |  |  |  |  | 1500 | 300 | 0 | Lake Forest | 0 | 0
6 |  | Furnish & install Countdown Ped Head System | EA | 6 | 135 | 145 |  |  |  |  | 1680 | 336 | 0 | Lake Forest | 0 | 0
7 | Arbor Way | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3500 |  |  |  |  | 4050 | 310 | 0 | Lake Forest | 0 | 0
8 |  | Furnish & install Actelis ML684DF Ethernet Switch | EA | 1 | 400 | 1100 |  |  |  |  | 1500 | 300 | 0 | Lake Forest | 0 | 0
9 |  | Furnish & install Countdown Ped Head System | EA | 6 | 135 | 145 |  |  |  |  | 1680 | 336 | 0 | Lake Forest
10 | Raymond Way | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3500 |  |  |  |  | 4050 | 310 | 0 | Lake Forest | Total | Total
11 |  | Furnish & install Actelis ML684DF Ethernet Switch | EA | 1 | 400 | 1100 |  |  |  |  | 1500 | 300 | 0 | Lake Forest | 0 | 0
12 |  | Furnish & install Countdown Ped Head System | EA | 8 | 135 | 145 |  |  |  |  | 2240 | 448 | 0 | Lake Forest | 0 | 0
13 | Muirlands Boulevard | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3500 |  |  |  |  | 4050 | 310 | 0 | Lake Forest | 0 | 0
14 |  | Furnish & install Actelis ML684DF Ethernet Switch | EA | 1 | 400 | 1100 |  |  |  |  | 1500 | 300 | 0 | Lake Forest | 0 | 0
15 |  | Furnish & install Countdown Ped Head System | EA | 8 | 135 | 145 |  |  |  |  | 2240 | 448 | 0 | Lake Forest
16 | Jeronimo Road | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3500 |  |  |  |  | 4050 | 310 | 0 | Lake Forest | Total | Total
17 |  | Furnish & install Actelis ML688 Ethernet Switch | EA | 1 | 400 | 2000 |  |  |  |  | 2400 | 480 | 0 | Lake Forest | 0 | 0
18 |  | Furnish & install Countdown Ped Head System | EA | 8 | 135 | 145 |  |  |  |  | 2240 | 448 | 0 | Lake Forest
19 | Toledo Way | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3400 |  |  |  |  | 3950 | 790 | 0 | Lake Forest
20 |  | Furnish & install Actelis ML688 Ethernet Switch | EA | 1 | 400 | 2000 |  |  |  |  | 2400 | 480 | 0 | Lake Forest
21 |  | Furnish & install Countdown Ped Head System | EA | 8 | 135 | 145 |  |  |  |  | 2240 | 448 | 0 | Lake Forest
22 | Serrano Road | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3500 |  |  |  |  | 4050 | 310 | 0 | Lake Forest
23 |  | Furnish & install Actelis ML684DF Ethernet Switch | EA | 1 | 400 | 1100 |  |  |  |  | 1500 | 300 | 0 | Lake Forest
24 |  | Furnish & install Countdown Ped Head System | EA | 8 | 135 | 145 |  |  |  |  | 2240 | 448 | 0 | Lake Forest
25 |  | Furnish & install P44 Cabinet on existing foundation | EA | 1 | 3200 | 19400 |  |  |  |  | 22600 | 4520 | 0 | Lake Forest
26 | From Serrano Road to Trabuco Road | Furnish & install 72 SMFO cable in existing conduit (Serrano to Trabuco) | LF | 1400 | 2.75 | 2 |  |  |  |  | 6650 | 1330 | 0 | Lake Forest
27 |  | Furnish & install 6E concrete pullboxes at each intersection (Serrano to Trabuco) | LS | 1 | 1465 | 420 |  |  |  |  | 1885 | 377 | 0 | Lake Forest
28 | Trabuco Road | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3500 |  |  |  |  | 4050 | 310 | 0 | Lake Forest
29 |  | Furnish & install Actelis ML684DF Ethernet Switch | EA | 1 | 400 | 1100 |  |  |  |  | 1500 | 300 | 0 | Lake Forest
30 |  | Furnish & install Countdown Ped Head System | EA | 8 | 135 | 145 |  |  |  |  | 2240 | 448 | 0 | Lake Forest
31 | Aliso Park Drive | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3500 |  |  |  |  | 4050 | 310 | 0 | Lake Forest
32 |  | Furnish & install Actelis ML684DF Ethernet Switch | EA | 1 | 400 | 1100 |  |  |  |  | 1500 | 300 | 0 | Lake Forest
33 |  | Furnish & install Countdown Ped Head System | EA | 8 | 135 | 145 |  |  |  |  | 2240 | 448 | 0 | Lake Forest
34 |  | Furnish & install P44 Cabinet on existing foundation | EA | 1 | 3200 | 19400 |  |  |  |  | 22600 | 4520 | 0 | Lake Forest
35 | Northcrest Drive | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3500 |  |  |  |  | 4050 | 310 | 0 | Lake Forest
36 |  | Furnish & install Actelis ML684DF Ethernet Switch | EA | 1 | 400 | 1100 |  |  |  |  | 1500 | 300 | 0 | Lake Forest
37 |  | Furnish & install Countdown Ped Head System | EA | 8 | 135 | 145 |  |  |  |  | 2240 | 448 | 0 | Lake Forest
38 |  | Furnish & install P44 Cabinet on existing foundation | EA | 1 | 3200 | 19400 |  |  |  |  | 22600 | 4520 | 0 | Lake Forest
39 | Normandale Drive | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3500 |  |  |  |  | 4050 | 310 | 0 | Lake Forest
40 |  | Furnish & install Actelis ML684DF Ethernet Switch | EA | 1 | 400 | 1100 |  |  |  |  | 1500 | 300 | 0 | Lake Forest
41 |  | Furnish & install Countdown Ped Head System | EA | 8 | 135 | 145 |  |  |  |  | 2240 | 448 | 0 | Lake Forest
42 | Portola Parkway | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3500 |  |  |  |  | 4050 | 310 | 0 | Lake Forest
43 |  | Furnish & install Actelis ML684DF Ethernet Switch | EA | 1 | 400 | 1100 |  |  |  |  | 1500 | 300 | 0 | Lake Forest
44 |  | Furnish & install Countdown Ped Head System | EA | 8 | 135 | 145 |  |  |  |  | 2240 | 448 | 0 | Lake Forest
45 |  | Furnish & install P44 Cabinet on existing foundation | EA | 1 | 3200 | 23000 |  |  |  |  | 26200 | 5240 | 0 | Lake Forest
46 | Pheasant Run | Furnish & install Cobalt ATC controller unit (No touchscreen) | EA | 1 | 550 | 3500 |  |  |  |  | 4050 | 310 | 0 | Lake Forest
47 |  | Furnish & install Actelis ML688 Ethernet Switch | EA | 1 | 400 | 2000 |  |  |  |  | 2400 | 480 | 0 | Lake Forest
48 |  | Furnish & install Countdown Ped Head System | EA | 8 | 135 | 145 |  |  |  |  | 2240 | 448 | 0 | Lake Forest
49 |  | Furnish & install Sierra Wireless Airlink GX440 Cell Modem | EA | 1 | 800 | 1200 |  |  |  |  | 2000 | 400 | 0 | Lake Forest
50 | From Trabuco Road to Portola Parkway | Furnish & install 3" Schedule 80 conduit and #6 concrete pullboxes spaced 500-ft O.C. | LF | 12500 | 22 | 12.5 |  |  |  |  | 431250 | 86250 | 0 | Lake Forest
51 |  | Furnish & install 72 SMFO cable in existing conduit (Trabuco to Portola) | LF | 15200 | 2.75 | 2 |  |  |  |  | 72200 | 14440 | 0 | Lake Forest
52 | Lake Forest TMC | Centracs License provided by Lake Forest as In-Kind Match | EA | 1 | 0 | 25000 |  |  |  |  | 25000 | 0 | 25000 | Lake Forest
53 | Marguerite Parkway | Furnish & install Active Pedestrian Safety System and Audio Push Buttons (6-ways) | LS | 1 | 3200 | 5800 |  |  |  |  | 9000 | 1800 | 0 | Mission Viejo
54 | Painted Trails | Furnish & install Active Pedestrian Safety System and Audio Push Buttons (2-ways) | LS | 1 | 1100 | 1250 |  |  |  |  | 2350 | 470 | 0 | Mission Viejo
55 | Wandering Trails | Furnish & install Active Pedestrian Safety System and Audio Push Buttons (2-ways) | LS | 1 | 1100 | 4250 |  |  |  |  | 5350 | 0 | 0 | Mission Viejo
56 | Glenn Ranch Road | Furnish & install Active Pedestrian Safety System and Audio Push Buttons (4-ways) | LS | 1 | 2200 | 5000 |  |  |  |  | 7200 | 0 | 0 | Mission Viejo
57 |  | Furnish & install Clary SP1250LX w/6 batteries UPS | EA | 1 | 1100 | 12000 |  |  |  |  | 13100 | 2620
58 | From Marguerite Parkway and Glenn Ranch Road | Furnish & install 72 SMFO cable in existing conduit (Marguerite to Glenn Ranch) | LF | 7500 | 2.75 | 2 |  |  |  |  | 35625 | 0 | 0 | Mission Viejo
59 |  | Furnish & install 12 fiber breakout cables at 5 intersections, splice into trunk and install 5 termination panels in controller cabinets | EA | 800 | 12 | 4 |  |  |  |  | 12800 | 0 | 0 | Mission Viejo
60 |  | Furnish & install 6E concrete pullboxes at each intersection (Trabuco to Portola) | EA | 4 | 1000 | 475 |  |  |  |  | 5900 | 1180 | 0 | Mission Viejo
61 | Valley Vista Way | Furnish & install new cabinet on existing foundation per County specifications. (Includes new Cobalt controller) | EA | 1 | 3300 | 24000 |  |  |  |  | 27300 | 5460 | 0 | County of Orange
62 |  | Furnish & install external UPS cabinet for Clary 1250 PD Plus UPS w/6 batteries | EA | 1 | 1100 | 12000 |  |  |  |  | 13100 | 2620 | 0 | County of Orange
63 |  | Furnish & install Actelis ML688 Ethernet Switch | EA | 1 | 400 | 2000 |  |  |  |  | 2400 | 480 | 0 | County of Orange
64 |  | Furnish & install Sierra Wireless Airlink GX440 Cell Modem | EA | 1 | 800 | 1200 |  |  |  |  | 2000 | 0 | 0 | County of Orange
65 |  | Add intersection to Centracs | EA | 1 | 250 | 0 |  |  |  |  | 250 | 50 | 0 | County of Orange
66 | Avenida De La Carlotta / El Toro | Furnish & Install Cobalt ATC controller unit | EA | 1 | 550 | 4200 |  |  |  |  | 4750 | 45 | 0 | Laguna Hills
67 | Avenida De La Carlotta / SB Ramps | Furnish & Install Cobalt ATC controller unit | EA | 1 | 550 | 4200 |  |  |  |  | 4750 | 950 | 0 | Laguna Hills
Subtotal: | [10 empty] | 888840 | 152768 | 25000
Contingency (10%): | [10 empty] | 88884 | 17776.8 | 0
Construction Management (15%): | [10 empty] | 133326 | 26665.2 | 0
SYSTEM IMPROVEMENT TOTAL: | [10 empty] | 1111050 | 197210 | 25000 |  | 0 | 0
Note on N3: Amy Tran: If the City is going to do the install or provide the equipment, input in this column
Note on N55: Amy Tran: Lake Forest will provide the Centracs license as in-kind match

## Section 6
SECTION 6: PROJECT SCHEDULE BY TASK
Project start date: January 1, 2020
Project end date: December 31, 2022
Primary Implementation
Task | Starting Date | Ending Date
a. Project Administration | 2020-01-01 | 2020-12-31
b. Developing and implementing optimized signal synchronization timing | 2020-01-01 | 2020-12-31
c. Producing a before and after study | 2020-01-01 | 2020-12-31
d. Engineering design of Signal Systems Improvement | 2020-01-01 | 2020-12-31
e. System integration | 2020-01-01 | 2020-12-31
f. Proposed Signal System Improvements, Construction Support/Inspection, and Contingency Costs | 2020-01-01 | 2020-12-31
g. Contingency | 2020-01-01 | 2020-12-31
h. Construction management | 2020-01-01 | 2020-12-31
i. Producing a Final Report | 2020-01-01 | 2020-12-31
Ongoing Monitoring and Maintenance
Task | Starting Date | Ending Date
a. Monitoring and improving optimized signal timing | 2021-01-01 | 2022-12-31
b. Communications and detection support | 2021-01-01 | 2022-12-31
c. OMM Memo | 2021-01-01 | 2022-12-31

## Section 7-Match
SECTION 7: DETAILED LOCAL MATCH COMMITMENT | [5 empty] | Input Only
Auto-Fill
PART 1: AGENCY TOTAL MATCH SUMMARY
Agency | CASH |  | IN-KIND |  | TOTAL MATCH
| PI | OMM | PI | OMM | PI | OMM
City of Lake Forest | 187556 | 7200 | 25000 | 0 | 212556 | 7200
| 194756 |  | 25000 |  | 219756
City of Mission Viejo | 41142 | 1920 | 3328 | 0 | 44470 | 1920
| 43062 |  | 3328 |  | 46390
County of Orange | 11486 | 480 | 0 | 0 | 11486 | 480
| 11966 |  | 0 |  | 11966
[5 empty] | 0 | 0
| 0 |  | 0 |  | 0
TOTAL MATCH | 240184 | 9600 | 28328 | 0 | 268512 | 9600
| 249784 |  | 28328 |  | 278112
PART 2: MATCH BREAKDOWN (CASH vs IN-KIND SERVICES)
A. Cash Match
Agency | Funding Source | Amount of Cash Contribution
City of Lake Forest | Local Funds | 194756
City of Mission Viejo | Local Funds | 43062
County of Orange | Road Funds | 11966
TOTAL CASH MATCH: |  | 249784
B. In-Kind Services
i. Specific Improvements (List items and Cost):
Agency | Description | Expenditure
City of Lake Forest | CENTRACS Licenses | 25000
Total Specific Improvements (i): |  | 25000
ii. Staffing Commitment:
Agency | Staff Position | Type of Service to Project |  | No. of Hours | Fully Burdened Hourly Rate | Total*
City of Mission Viejo | Traffic Engineer | Project Administration, Quality Assurance & Signal Timing |  | 10 | 145 | 1450
| Transportation Analyst | Signal Timing Implementation & Operations |  | 9 | 94 | 846
| PW Inspector | Project Administration, Quality Assurance & Signal Timing |  | 2 | 124 | 248
| Traffic Systems Specialist (HCI) | Signal Timing Implementation & Operations |  | 4 | 115 | 460
| Information Technology Manager | Review of Fiber Design plans, meeting participation, and system integration |  | 2 | 96 | 192
| Information Technology Manager | Review of Fiber Design plans, meeting participation, and system integration |  | 2 | 66 | 132
Total for City of Mission Viejo: | [5 empty] | 3328
0
Total for City of ___________: | [5 empty] | 0
Total Staffing Commitment (ii): | [5 empty] | 3328
TOTAL IN-KIND MATCH* (i + ii): | [5 empty] | 28328
*Total amount is the required participation by the identified agency. The number of hours and hourly rate will be based on each agency’s actual fully burdened billing rates, which must collectively equal the same value of the assigned “Total” dollars. Each agency will be responsible for keeping detailed records of hours worked and description of work. An accounting record of personnel, hours at fully burdened rate is expected to be included with the final submittal. Records will be subject to auditing.
Note on G46: Amy Tran: This is the total for (i) Specific Improvements + (ii) Staffing commitment

## Section 8 and 9
SECTION 8: ENVIRONMENTAL CLEARANCE AND OTHER PERMITS
Environmental clearance and other permits (if needed) will be obtained for this project.
SECTION 9: SELECTION CRITERIA CALCULATIONS
Vehicle Miles Traveled (VMT):
| Segment | ADTs | Distance | VMT
| Bridger Road to Rockfield Boulevard | 62100 | 0.16 | 9936
| Rockfield Boulevard to Arbor Way | 47600 | 0.16 | 7616
| Arbor Way to Raymond Way | 47600 | 0.18 | 8568
| Raymond Way to Muirlands Boulevard | 47600 | 0.27 | 12852
| Muirlands Boulevard to Jeronimo Road | 39900 | 0.53 | 21147
| Jeronimo Road to Toledo Way | 35200 | 0.4 | 14080
| Toledo Way to Serrano Road | 34200 | 0.24 | 8208
| Serrano Road to Trabuco Road | 34300 | 0.2 | 6860
| Trabuco Road to Aliso Park Drive | 31300 | 0.38 | 11894
| Aliso Park Drive to Northcrest Drive | 25500 | 0.48 | 12240
| Northcrest Drive to Normandale Drive | 23200 | 0.97 | 22504
| Normandale Drive to Santa Margarita Parkway | 23100 | 0.53 | 12243
| Santa Margarita Parkway to Phesant Run | 24300 | 0.24 | 5832
| Pheasant Run to Marguerite Parkway | 13000 | 0.39 | 5070
| Marguerite Parkway to Painted Trails | 14700 | 0.6 | 8820
| Painted Trails to Wandering Trails | 14700 | 0.26 | 3822
| Wandering Trails to Glenn Ranch Road | 14700 | 0.12 | 1768
| Glenn Ranch Road to Valley Vista Way | 12300 | 0.37 | 4551
| Valley Vista Way to Ridgeline Road | 12300 | 0.55 | 6765
| Total Project VMT: |  | 7.03 | 184776
Source: 2014 City of Lake Forest and 2015 City of Mission Viejo ADT Counts

## Calc Est Points
Calculations and Estimated Points
Criteria (Max Points) | Estimated Points
1. Vehicle Miles Traveled (VMT) (20 points) | 10
VMT = 184,776 (See VMT Table)
2. Cost Benefit Ratio: (15 points) | 8
Calculation for Total Project Cost / VMT = $1,390,559/184,776 = 7.5
3. Project Characteristics: (10 points) | 9
New or upgraded communication systems (2); Intersection / field system modernization and replacement (2); new or upgraded detection (1); TMC (4)
4. Transportation Significance (10 points) | 5
Signal Synchronization Network
5. Maintenance of Effort: (5 points) | 0
0 years beyond 3 year grant period
6. Project Scale: (10 points) | 5
a. Number of signals = 22
b. Number of signals being synchronized / Total number of corridor signals= 22/39=56.4%
7. Number of Jurisdictions: (20 points) | 16
4 Jurisdictions
8. Current Project Readiness (5 points) | 5
Project start date: January 1, 2020
9. Funding Match: (5 points) | 0
278,112 / $1,390,559 = 20%= 20%
Total Points | 58

## Section 10
SECTION 10: DETAILED BREAKDOWN OF COSTS BY AGENCIES
City of Lake Forest
Number of Signals: |  | 15
Project Tasks (Lake Forest) |  |  |  |  | Total Cost | Match
[6 empty] | Cash | In-Kind
Task 1: Project Administration |  |  |  |  | 15000 | 3000 | 0
Task 2: Data Collection |  |  |  |  | 6900 | 1380 | 0
Task 3: Field Review and Plans Specifications, and Estimates |  |  |  |  | 100000 | 20000 | 0
Task 4: Corridor "Before" Study |  |  |  |  | 5000 | 1000 | 0
Task 5: Signal Timing Optimization and Implementation |  |  |  |  | 60000 | 12000 | 0
Task 6: Corridor "After" Study |  |  |  |  | 5000 | 1000 | 0
Task 7: Synchronization System Construction (See Table II) |  |  |  |  | 865880 | 148176 | 25000
Task 8: Project Report |  |  |  |  | 5000 | 1000 | 0
Task 9: Ongoing Operations & Maintenance (See Task 9 Details) |  |  |  |  | 36000 | 7200 | 0
Total Project Cost: |  |  |  |  | 1098780 | 194756 | 25000
City of Mission Viejo
Number of Signals: |  | 4
Project Tasks (Mission Viejo) |  |  |  |  | Total Cost | Match
[6 empty] | Cash | In-Kind
Task 1: Project Administration |  |  |  |  | 4000 | 0 | 800
Task 2: Data Collection |  |  |  |  | 2050 | 410 | 0
Task 3: Field Review and Plans Specifications, and Estimates |  |  |  |  | 20000 | 2778 | 1222
Task 4: Corridor "Before" Study |  |  |  |  | 1500 | 300 | 0
Task 5: Signal Timing Optimization and Implementation |  |  |  |  | 16000 | 1894 | 1306
Task 6: Corridor "After" Study |  |  |  |  | 1500 | 300 | 0
Task 7: Synchronization System Construction (See Table II) |  |  |  |  | 176300 | 35260 | 0
Task 8: Project Report |  |  |  |  | 1000 | 200 | 0
Task 9: Ongoing Operations & Maintenance (See Task 9 Details) |  |  |  |  | 9600 | 1920 | 0
Total Project Cost: |  |  |  |  | 231950 | 43062 | 3328
County of Orange
Number of Signals: |  | 1
Project Tasks (County of Orange) |  |  |  |  | Total Cost | Match
[6 empty] | Cash | In-Kind
Task 1: Project Administration |  |  |  |  | 1000 | 200 | 0
Task 2: Data Collection |  |  |  |  | 350 | 70 | 0
Task 3: Field Review and Plans Specifications, and Estimates |  |  |  |  | 500 | 100 | 0
Task 4: Corridor "Before" Study |  |  |  |  | 400 | 80 | 0
Task 5: Signal Timing Optimization and Implementation |  |  |  |  | 3500 | 700 | 0
Task 6: Corridor "After" Study |  |  |  |  | 400 | 80 | 0
Task 7: Synchronization System Construction (See Table II) |  |  |  |  | 51079 | 10215.8 | 0
Task 8: Project Report |  |  |  |  | 200 | 40 | 0
Task 9: Ongoing Operations & Maintenance (See Task 9 Details) |  |  |  |  | 2400 | 480 | 0
Total Project Cost: |  |  |  |  | 59829 | 11965.8 | 0
Project Summary
X | All guidelines were met for this project.
Not all qualifications were met. An explanation of why the guidelines were not met for this project is provided below.
LIST OF CONTACTS
Agency |  |  | Phone | Email |  | Street Address
City of Lake Forest Dave Rogers Traffic Engineering Manager |  |  | 949-461-3485 | drogers@lakeforestca.gov |  | City of Lake Forest 25550 Commercentre Dr Suite 100 Lake Forest, CA 92630
City of Mission Viejo Philip Nitollama Traffic Engineer |  |  | 949-470-3068 | pnitollama@cityofmissionviejo.org |  | City of Mission Viejo 200 Civic Center Mission Viejo, CA 92691
Couty of Orange Wei Zhu Civil Engineer, Project Mgmt |  |  | 714-647-3976 | wei.zhu@ocpw.ocgov.com |  | County of Orange 300 N. Flower Street Santa Ana, CA 92703